## CostEstimate_Template
Activity | Resource | Effort Estimate per Role (hours) | Hourly Rate | Cost per Role | Cost per Activity | Cost per Phase | % of Total Cost per Phase | 250000 | Budget | Role and Rate table
1. Initiation Phase | [9 empty] | PM | 70
Developing the project charter | PM | 15 | 70 | 1050 | 1050 | 1050 |  |  |  | BA | 40
Building and confirming the project team | BA | 8 | 40 | 320 | 320 | 320 |  |  |  | Developer | 50
Developing the project management plan | PM | 25 | 70 | 1750 | 1750 | 1750 |  |  |  | SME | 40
Create risk register and initial risk workshop | PM | 15 | 70 | 1050 | 1050 | 1050 |  |  |  | External Consultant | 150
Scheduling analysis and design workshops | PM | 5 | 70 | 350 | 350 | 350
Identifying stakeholders and defining their roles and responsibilities | PM | 5 | 70 | 350 | 350 | 350
Establishing project governance and escalation structures | PM | 5 | 70 | 350 | 350 | 350
Setting up project communication channels and reporting protocols | BA | 2 | 40 | 80 | 80 | 80
Phase Subtotal | [5 empty] | 5300 | 2.12%
2. Analysis and Design Phase
Conducting as-is process analysis for current sales operations | PM | 15 | 70 | 1050 | 1050 | 1050
| BA | 30 | 40 | 1200 | 1200 | 1200
| External Consultant | 20 | 150 | 3000 | 3000 | 3000
Activity Subtotal |  |  |  |  | 5250
Developing detailed business and functional requirement documents | BA | 50 | 40 | 2000 | 2000 | 2000
| External Consultant | 20 | 150 | 3000 | 3000 | 3000
Activity Subtotal |  |  |  |  | 5000
Securing stakeholder review and approval of requirements | PM | 15 | 70 | 1050 | 1050 | 1050
Conducting future state design sessions | External Consultant | 45 | 150 | 6750 | 6750 | 6750
| SME | 30 | 40 | 1200 | 1200 | 1200
Activity Subtotal |  |  |  |  | 7950
Developing solution design documents and obtaining formal sign-off | BA | 30 | 40 | 1200 | 1200 | 1200
| External Consultant | 15 | 150 | 2250 | 2250 | 2250
Activity Subtotal |  |  |  |  | 3450
Preparing a detailed build plan and timeline | PM | 10 | 70 | 700 | 700 | 700
Coordinating access to CRM environments and required tools | Developer | 20 | 50 | 1000 | 1000 | 1000
Establishing a change control process | BA | 10 | 40 | 400 | 400 | 400
Performing risk analysis and documenting mitigation strategies | BA | 15 | 40 | 600 | 600 | 600
Phase Subtotal | [5 empty] | 25400 | 10.16%
3. Build Phase
Configuring CRM system features and workflows | Developer | 120 | 50 | 6000 | 6000 | 6000
| External Consultant | 60 | 150 | 9000 | 9000 | 9000
Activity Subtotal |  |  |  |  | 15000
Developing custom configurations and enhancements | Developer | 140 | 50 | 7000 | 7000 | 7000
| External Consultant | 50 | 150 | 7500 | 7500 | 7500
Activity Subtotal |  |  |  |  | 14500
Creating dashboards and standard reports | Developer | 80 | 50 | 4000 | 4000 | 4000
| SME | 20 | 40 | 800 | 800 | 800
Activity Subtotal |  |  |  |  | 4800
Performing data migration and validation activities | Developer | 100 | 50 | 5000 | 5000 | 5000
| External Consultant | 80 | 150 | 12000 | 12000 | 12000
Activity Subtotal |  |  |  |  | 17000
Developing and configuring system integrations | Developer | 100 | 50 | 5000 | 5000 | 5000
| External Consultant | 80 | 150 | 12000 | 12000 | 12000
Activity Subtotal |  |  |  |  | 17000
Conducting unit testing for all configured and developed components | Developer | 100 | 50 | 5000 | 5000 | 5000
Reviewing and obtaining approval of test scripts from business stakeholders | BA | 20 | 40 | 800 | 800 | 800
Preparing deployment and rollback plans | PM | 15 | 70 | 1050 | 1050 | 1050
Phase Subtotal | [5 empty] | 75150 | 30.06%
4. Testing Phase
Conducting system testing to validate end-to-end functionality | Developer | 100 | 50 | 5000 | 5000 | 5000
| External Consultant | 50 | 150 | 7500 | 7500 | 7500
Activity Subtotal |  |  |  |  | 12500
Performing integration testing with existing internal systems | Developer | 50 | 50 | 2500 | 2500 | 2500
| External Consultant | 50 | 150 | 7500 | 7500 | 7500
Activity Subtotal |  |  |  |  | 10000
Conducting user acceptance testing with sales representatives and managers | SME | 60 | 40 | 2400 | 2400 | 2400
| BA | 25 | 40 | 1000 | 1000 | 1000
Activity Subtotal |  |  |  |  | 3400
Allocating time for defect resolution and regression testing | Developer | 70 | 50 | 3500 | 3500 | 3500
| BA | 30 | 40 | 1200 | 1200 | 1200
Activity Subtotal |  |  |  |  | 4700
Developing end-user training materials | BA | 50 | 40 | 2000 | 2000 | 2000
| SME | 40 | 40 | 1600 | 1600 | 1600
Activity Subtotal |  |  |  |  | 3600
Finalizing system documentation and support guides | BA | 30 | 40 | 1200 | 1200 | 1200
Preparing production environments for deployment | Developer | 30 | 50 | 1500 | 1500 | 1500
Phase Subtotal | [5 empty] | 36900 | 14.76%
5. Deployment Phase
Executing final data migration activities | Developer | 20 | 50 | 1000 | 1000 | 1000
| External Consultant | 30 | 150 | 4500 | 4500 | 4500
Activity Subtotal |  |  |  |  | 5500
Migrating configurations and data to the production environment | Developer | 40 | 50 | 2000 | 2000 | 2000
Delivering training sessions to end users | SME | 100 | 40 | 4000 | 4000 | 4000
| PM | 15 | 70 | 1050 | 1050 | 1050
Activity Subtotal |  |  |  |  | 5050
Executing the deployment plan | PM | 20 | 70 | 1400 | 1400 | 1400
| External Consultant | 10 | 150 | 1500 | 1500 | 1500
Activity Subtotal |  |  |  |  | 2900
Go-live readiness review and monitor | PM | 15 | 70 | 1050 | 1050 | 1050
Monitoring system performance and stability after go-live | Developer | 40 | 50 | 2000 | 2000 | 2000
Establishing a help desk and support model for end users | BA | 40 | 40 | 1600 | 1600 | 1600
Phase Subtotal | [5 empty] | 20100 | 8.04%
6. Closeout Phase
Providing post-deployment support as users begin using the CRM system | Developer | 40 | 50 | 2000 | 2000 | 2000
| SME | 40 | 40 | 1600 | 1600 | 1600
Activity Subtotal |  |  |  |  | 3600
Transitioning system ownership to the support and operations teams | PM | 15 | 70 | 1050 | 1050 | 1050
Conducting lessons learned sessions with project stakeholders | PM | 15 | 70 | 1050 | 1050 | 1050
Closing vendor and consulting contracts | PM | 10 | 70 | 700 | 700 | 700
| External Consultant | 8 | 150 | 1200 | 1200 | 1200
Activity Subtotal |  |  |  |  | 1900
Documenting final project outcomes and key learnings | PM | 30 | 70 | 2100 | 2100 | 2100
Releasing project resources and formally closing the project | PM | 10 | 70 | 700 | 700 | 700
Phase Subtotal | [5 empty] | 10400 | 4.16%
First-year Subscription | [5 empty] | 50000 | 20%
Project Contingencies | [5 empty] | 25000 | 10%
Total Cost Estimate | [5 empty] | 248250 | 99.3%