Project Scope Statement

Project Title: SalesFlow CRM Implementation at BrightWave Solutions

Date: Mar 1 				Prepared by: Emily Carter (Project Manager)

Project Summary and Justification:

BrightWave Solutions is experiencing limited pipeline visibility, inconsistent sales processes, missed follow-ups with potential clients. The current tools just supported the basic tracking, becoming difficult to manage the growing sales happening. CEO Daniel Harper approved implementing the SalesFlow CRM system to improve sales productivity by 25% by automating tracking, centralizing customer and opportunity data, and providing real-time dashboards for analyzing.

The project budget is $250,000 (Year 1 subscription $50,000 paid upfront, $100,000 external consulting for implementation and data migration, and $100,000 internal labor for configuration, testing, training, and change management). After that, annual subscription renewals of $50,000 per year will be paid in future fiscal years and not included in the initial budget. Expected benefits include improved forecast accuracy, fewer lost opportunities from missed follow-ups, and approximately 25% higher sales productivity through reduced manual data entry and reporting.

System Characteristics and Requirements:

- Customer and opportunity data model (Functional/Data): One shared database for accounts, contacts, opportunities, and activities with standard required fields and naming.

- Task management and follow-up reminders (Functional): Create tasks, send reminders, and flag overdue follow-ups.

- Pipeline visibility and dashboards (Functional): Real-time dashboards for pipeline value, opportunity aging, stage conversion, and forecasting.

- Forecasting and reporting (Functional): Standard reports available weekly and on demand without manual spreadsheet consolidation.

- Security and access controls (Non-functional): Role-based access for representatives, managers, sales operations, and executives.

- Integrations and data synchronization (Interface): Support approved synchronization with internal systems (nightly/daily sync).

- Usability (Non-functional): Quick search and easy interaction logging.

- Availability (Non-functional): Available 24/7 with planned maintenance, acceptable response time for dashboards and records.

- Data migration and cleansing (Transition): Map, deduplicate, cleanse, migrate, and validate customer and opportunity data from shared folders.

- Training and go-live support (Transition): Role-based training, job aids, and a 30-day hypercare period after go-live.

Summary of Project Deliverables:

Project management deliverables: project charter, project scope statement, work breakdown structure (WBS), detailed project plan, project cost estimate and budget, risk management plan, stakeholder management plan, regular project status reports, business and technical design documents, system configuration documentation, test plans and test scripts, training materials, and user reference guides.

Product-related deliverables:

- Workshop outputs (As-Is and To-Be sales process maps, data definitions, and reporting needs).

- Configured SalesFlow CRM instance (fields, workflows, stages, templates, roles, and dashboards).

- Data migration package (mapping, cleansing rules, deduplication approach) and validated migrated datasets.

- Reporting and dashboard pack for sales managers and executives.

- Testing artifacts and UAT sign-off.

- Training materials and job aids (role-based guides) plus training completion tracking.

- Cutover and go-live checklist with rollback and support procedures.

- 30-day hypercare support plan (Aug 3 to Sep 3) with issue triage and stabilization.

- Benefits measurement plan to track adoption, time saved, and forecast accuracy.

Project Success Criteria: Our goal is to complete this project from March 2, 2026 through September 3, 2026 with go-live on August 3, 2026, for no more than $250,000. Success will be measured by meeting approved scope requirements, passing UAT, completing accurate data migration with minimal duplicates or errors, delivering real-time dashboards for managing, and achieving 90% user adoption within 30 days after go-live. Leadership expects the CRM to deliver productivity and forecasting improvements and to pay for itself within 12 months after go-live.

Constraints, Boundaries, and Assumptions:
This project must meet the approved schedule and budget, with a fixed go-live date of August 3, 2026 and a budget cap of $250,000. The plan will treat Memorial Day and Independence Day as non-working days, and we will follow a waterfall approach with phase approvals; testing must be finished before go-live. The scope is limited to implementing SalesFlow CRM for the sales team and does not include advanced analytics customization beyond standard dashboards, extra integrations with external marketing tools, or adding customer support/finance users in the first rollout. For testing, UAT will include the Sales Ops SME, selected sales reps, sales managers, and IT only. We assume internal systems can provide usable data for integration/sync, the SME provides complete requirements on time, users will adopt the system, and CRM data will follow company security and privacy rules.